## Sprint
|  |  |  | Week #1 (2 hrs / week) | [6 empty] | Week #2 (2 hrs / week) | [6 empty] | Week #3 (2 hrs / week) | [6 empty] | Week #4 (2 hrs / week) | [6 empty] | Week #5 (2 hrs / week) | [6 empty] | Week #6 (2 hrs / week) | [6 empty] | Week #7 (2 hrs / week) | [6 empty] | Week #8 (2 hrs / week) | [6 empty] | Week #9 (2 hrs / week) | [6 empty] | Week #10 (2 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = Number of weeks x Number of hours per week) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70
 | time axis 2020-03-02 to 2020-05-10
|  |  |  | 80 | 78.86 | 77.72 | 76.58 | 75.44 | 74.3 | 73.16 | 72.02 | 70.88 | 69.74 | 68.6 | 67.46 | 66.32 | 65.18 | 64.04 | 62.9 | 61.76 | 60.62 | 59.48 | 58.34 | 57.2 | 56.06 | 54.92 | 53.78 | 52.64 | 51.5 | 50.36 | 49.22 | 48.08 | 46.94 | 45.8 | 44.66 | 43.52 | 42.38 | 41.24 | 40.1 | 38.96 | 37.82 | 36.68 | 35.54 | 34.4 | 33.26 | 32.12 | 30.98 | 29.84 | 28.7 | 27.56 | 26.42 | 25.28 | 24.14 | 23 | 21.86 | 20.72 | 19.58 | 18.44 | 17.3 | 16.16 | 15.02 | 13.88 | 12.74 | 11.6 | 10.46 | 9.32 | 8.18 | 7.04 | 5.9 | 4.76 | 3.62 | 2.48 | 0
|  |  | 80 | 80 | 77 | 75 | 73 | 71 | 71 | 70 | 70 | 68 | 66 | 64 | 61 | 60 | 60 | 60 | 58 | 56 | 55 | 54 | 52 | 51 | 50 | 47 | 45 | 42 | 40 | 37 | 35 | 34 | 33 | 33 | 32 | 30 | 29 | 27 | 27 | 27 | 25 | 25 | 24 | 23 | 23 | 23 | 21 | 20 | 19 | 18 | 18 | 18 | 18 | 18 | 18 | 16 | 15 | 15 | 15 | 15 | 13 | 12 | 10 | 10 | 10 | 8 | 8 | 7 | 5 | 4 | 2 | 0 | 0
User Stories Definition | Define User Stories | Harsh | 4 | 2020-03-02: 20; 2020-03-03: 19; 2020-03-04: 18; 2020-03-05: 17; 2020-03-06: 16; 2020-03-07: 16; 2020-03-08: 16
| Breakdown user Stories into tasks | Vijayashree | 2 | 2020-03-02: 18; 2020-03-03: 18; 2020-03-04: 17; 2020-03-05: 17; 2020-03-06: 16; 2020-03-07: 16; 2020-03-08: 16
| Define User Stories | Jojo | 2 | 2020-03-02: 22; 2020-03-03: 20; 2020-03-04: 20; 2020-03-05: 20; 2020-03-06: 20; 2020-03-07: 20; 2020-03-08: 19
| Breakdown user Stories into tasks | Varun | 1 | 2020-03-02: 20; 2020-03-03: 20; 2020-03-04: 20; 2020-03-05: 19; 2020-03-06: 19; 2020-03-07: 19; 2020-03-08: 19
Design for the project | Design User Interface | Harsh | 4 | 2020-03-09: 16; 2020-03-10: 15; 2020-03-11: 14; 2020-03-12: 13; 2020-03-13: 12; 2020-03-14: 12; 2020-03-15: 12
| Reservation System design tasks | Vijayashree | 4 | 2020-03-09: 16; 2020-03-10: 15; 2020-03-11: 14; 2020-03-12: 13; 2020-03-13: 12; 2020-03-14: 12; 2020-03-15: 12
| Reservation System | Jojo | 2 | 2020-03-09: 19; 2020-03-10: 19; 2020-03-11: 19; 2020-03-12: 19; 2020-03-13: 19; 2020-03-14: 18; 2020-03-15: 18
| DB schema analysis | Varun | 1 | 2020-03-09: 19; 2020-03-10: 19; 2020-03-11: 19; 2020-03-12: 19; 2020-03-13: 18; 2020-03-14: 18; 2020-03-15: 18
Back End Implementation | Back-End tasks Starter code for back end Basic Login endpoint User Registration endpoint | Jojo | 12 | 2020-03-16: 18; 2020-03-17: 17; 2020-03-18: 16; 2020-03-19: 15; 2020-03-20: 14; 2020-03-21: 13; 2020-03-22: 12; 2020-03-23: 11; 2020-03-24: 10; 2020-03-25: 10; 2020-03-26: 9; 2020-03-27: 9; 2020-03-28: 9; 2020-03-29: 9; 2020-03-30: 9; 2020-03-31: 9; 2020-04-01: 9; 2020-04-02: 8; 2020-04-03: 7; 2020-04-04: 7; 2020-04-05: 7; 2020-04-06: 7; 2020-04-07: 7; 2020-04-08: 6; 2020-04-09: 6; 2020-04-10: 6; 2020-04-11: 6; 2020-04-12: 6; 2020-04-13: 6; 2020-04-14: 6; 2020-04-15: 6; 2020-04-16: 6; 2020-04-17: 6; 2020-04-18: 6; 2020-04-19: 6
| Membership-fee Endpoints | Vijayashree | 7 | 2020-03-16: 12; 2020-03-17: 12; 2020-03-18: 12; 2020-03-19: 12; 2020-03-20: 12; 2020-03-21: 11; 2020-03-22: 11; 2020-03-23: 11; 2020-03-24: 11; 2020-03-25: 11; 2020-03-26: 11; 2020-03-27: 11; 2020-03-28: 10; 2020-03-29: 10; 2020-03-30: 10; 2020-03-31: 10; 2020-04-01: 10; 2020-04-02: 10; 2020-04-03: 9; 2020-04-04: 9; 2020-04-05: 9; 2020-04-06: 9; 2020-04-07: 9; 2020-04-08: 8; 2020-04-09: 8; 2020-04-10: 8; 2020-04-11: 7; 2020-04-12: 7; 2020-04-13: 7; 2020-04-14: 6; 2020-04-15: 6; 2020-04-16: 6; 2020-04-17: 5; 2020-04-18: 5; 2020-04-19: 5
| Back-End implementation | Varun | 0 | 2020-03-16: 18; 2020-03-17: 18; 2020-03-18: 18; 2020-03-19: 18; 2020-03-20: 18; 2020-03-21: 18; 2020-03-22: 18
| Mongo Documents sample for vehicle and user | Harsh | 2 | 2020-03-16: 12; 2020-03-17: 11; 2020-03-18: 10; 2020-03-19: 10; 2020-03-20: 10; 2020-03-21: 10; 2020-03-22: 10
Front-End Code Implementation | UI Tasks - 1 User profile Admin module Manage location Manage vehicles Manage user Manage bookings | Varun | 14 | 2020-03-23: 18; 2020-03-24: 17; 2020-03-25: 16; 2020-03-26: 15; 2020-03-27: 14; 2020-03-28: 13; 2020-03-29: 12; 2020-03-30: 11; 2020-03-31: 10; 2020-04-01: 10; 2020-04-02: 10; 2020-04-03: 10; 2020-04-04: 9; 2020-04-05: 8; 2020-04-06: 8; 2020-04-07: 8; 2020-04-08: 8; 2020-04-09: 8; 2020-04-10: 7; 2020-04-11: 7; 2020-04-12: 7; 2020-04-13: 7; 2020-04-14: 6; 2020-04-15: 5; 2020-04-16: 4; 2020-04-17: 4; 2020-04-18: 4; 2020-04-19: 4
| Front-End Implementation | Jojo | 0
| Front-End Implementation | Vijayashree | 0
| UI Tasks - 2 Register Login Car search Car booking Car alternative options User profile | Harsh | 7 | 2020-03-23: 10; 2020-03-24: 9; 2020-03-25: 8; 2020-03-26: 7; 2020-03-27: 6; 2020-03-28: 5; 2020-03-29: 4; 2020-03-30: 4; 2020-03-31: 4; 2020-04-01: 4; 2020-04-02: 4; 2020-04-03: 4; 2020-04-04: 4; 2020-04-05: 3; 2020-04-06: 3; 2020-04-07: 3; 2020-04-08: 3; 2020-04-09: 3; 2020-04-10: 3; 2020-04-11: 3; 2020-04-12: 3; 2020-04-13: 3; 2020-04-14: 3; 2020-04-15: 3; 2020-04-16: 3; 2020-04-17: 3; 2020-04-18: 3; 2020-04-19: 3
Deployment | Deployment on AWS, Dockerization | Jojo | 6 | 2020-04-20: 6; 2020-04-21: 6; 2020-04-22: 6; 2020-04-23: 5; 2020-04-24: 5; 2020-04-25: 5; 2020-04-26: 5; 2020-04-27: 5; 2020-04-28: 5; 2020-04-29: 4; 2020-04-30: 4; 2020-05-01: 4; 2020-05-02: 4; 2020-05-03: 3; 2020-05-04: 3; 2020-05-05: 3; 2020-05-06: 2; 2020-05-07: 2; 2020-05-08: 1; 2020-05-09: 0; 2020-05-10: 0
| Deployment | Varun | 3 | 2020-04-20: 3; 2020-04-21: 3; 2020-04-22: 3; 2020-04-23: 3; 2020-04-24: 3; 2020-04-25: 3; 2020-04-26: 3; 2020-04-27: 3; 2020-04-28: 2; 2020-04-29: 2; 2020-04-30: 2; 2020-05-01: 2; 2020-05-02: 2; 2020-05-03: 2; 2020-05-04: 2; 2020-05-05: 1; 2020-05-06: 1; 2020-05-07: 1; 2020-05-08: 1; 2020-05-09: 0; 2020-05-10: 0
| Diagrams | Harsh | 4 | 2020-04-20: 4; 2020-04-21: 4; 2020-04-22: 4; 2020-04-23: 4; 2020-04-24: 3; 2020-04-25: 3; 2020-04-26: 3; 2020-04-27: 3; 2020-04-28: 3; 2020-04-29: 3; 2020-04-30: 2; 2020-05-01: 2; 2020-05-02: 2; 2020-05-03: 2; 2020-05-04: 2; 2020-05-05: 2; 2020-05-06: 1; 2020-05-07: 0; 2020-05-08: 0; 2020-05-09: 0; 2020-05-10: 0
| Burndown chart | Vijayashree | 5 | 2020-04-20: 5; 2020-04-21: 5; 2020-04-22: 5; 2020-04-23: 4; 2020-04-24: 4; 2020-04-25: 4; 2020-04-26: 4; 2020-04-27: 4; 2020-04-28: 3; 2020-04-29: 3; 2020-04-30: 2; 2020-05-01: 2; 2020-05-02: 2; 2020-05-03: 1; 2020-05-04: 1; 2020-05-05: 1; 2020-05-06: 1; 2020-05-07: 1; 2020-05-08: 0; 2020-05-09: 0; 2020-05-10: 0
|  | Total hours spent | 80
Team:
Jojo | 2 hours / Week
Harsh | 2 hours / Week
Varun | 2 hours / Week
Vijayashree | 2 hours / Week
Total Available Hours During Sprint: | 80